OFFICE OF THE SECRETARY GOPINATH JUBA SANGHA

ALISISASAN, KHURDA, PIN- 752102, ORISSA.

PHONE NO- (0674)464017.

E-mail- gopinath_juba@yahoo.com

Or gd_mishra@yahoo.com

To

The Chair,

SEEDS

PORTLAND OR

USA.

Sub : Sending of quarterly pregress ,audit utilisation and impact reports of Gopinath Juba Sangh (GJS) for Rehabilitation of Super Cyclone Victims.

Sir,

We are attaching here with the detailed report as cited above for your kind information and necessary action.

Further we are to inform you that we are running the creche units through your project has been completed by 31st December,2002. If the grant for the creche units would not be sanctioned by  your organisation during 1st January,2002 to 31st December,2002 , we shall be compled to bear the cost from our own fund. This may kindly be clarified by your organisation through e-mail.

Thnaking you,

Yours faithfully

(Artratran Behera )

Secretary.

Encl : As abobe

QUARTERLY PROGRESS REPORT OF SEEDS PROJECTS

FROM 01.01.2002 TO 31.03.2002

(JANUARY-2002 –MARCH-2002)

01.	NAME AND ADDRESS OF THE 			GOPINATH JUBA SANGHA (GJS)

ORGANISATION.					At.- Alisisasan, Po- Darada,

Via- Balipatna. Dist: Khurda.

Pin- 752102. (ORISSA)

Ph- (0674)464017

E-Mail- gopinath_juba@yahoo.com

OR    gd_mishra@yahoo.com

02.	OPERATION OF THE PROJECT ARES		Darada, Hoikera & Dengasahi of

Pampalo G.P. under Balipatna Block

In Khurda District.

03.	DATE OF COMMENCEMENT OF THE		01.01.2001.

PROJECT.

04.	QUARTER UNDER REPORT			1st January to 31st March,2002.

- COVERAGE.

(a) Continuation of SHG				We have already formed 4 (four) nos.

SHGs like 2 nos Male & 2 nos Female SHGs.

The Group used to deposit their monthly

Subscription in the Bank regularly.

(b) Training to SHG					We have organized two-day Training

programme for SHG members.

© Creche Centre continuation			The 3 nos of Creche Centres are

continuing in Project Areas as :

- Darada

- Hoikera

- Dengasahi.

(d) Training to Creche workers			We have organized 3 days training programme

for Creche Workers with technical support from

the CYSD-DRTC (Dist-Resource Trg. Centre)

(e) Details categories Students list			      SC          OBC             GEN          TOTAL

Centrewise.					B+G=T         B+G=T       B+G=T       B+G=T

1- Darada         12+19=31      -                     -          12+19=31

2-Hoikera         10+07=17    6+7=13             -         16+14=30

3-engasahi        11+08=19    4+7=11           -           15+15=30

(f) Type of materials used in the center		We have purchased Teaching/Learning materials

like slates, pencils, chalk, story tellingcard, charts

etc  and developed low-cost/no- cost teaching/

learning aid for joyful learning.

(g)  Village Education Committee.			We have already formed 3 nos of VEC in 3

centers. They are totally responsible for smooth

running of Centres.

(h) Do the Creche Workers organize the		Yes., The Village Education Committee

regular meeting of VEC.			Meeting is being organized in every quarter where

teachers & parents, VEC members & GJS staff

remain present & discuss about learners’ progress.

Econimic & Social development work of the

Village

.

(i)  Monitory & Evaluation				The Secretary of the institution has monitored the

day-to-day activities of the programme for its

progress & proper implementation. The teacher

VEC members SHG members & GJS staff attend

The monthly review meeting and finalise the

Action plan to expedite the project smoothly.

QUARTERLY PROGRESS REPORT OF SEEDS PROJECT

FROM 01.04.2002-30.06.2002.

(APRIL – 02 TO JUNE – 02)

01.Name & Address of the                                     :  GOPINATH  JUBA  SANGHA,(GJS)

Organisation.                                                         At-Alisisan,Po-Darada,

Via-Balipatna,Dist-Khurda,

Pin-752102,Ph.No.0674/464017.

E-mail – gopinath_juba @yahoo.com

Or           gd_mishra@yahoo.com

02. Operation of the Project Area                           :    DARADA, HOIKERA & DENGASAHI of

Pampala G.P.under Balipatha

Block in Khurda District.

03. Date of the commencement of                          :     01.01.2001.

the Project.

04. Quarter under Report                                        :     1st April-2002 to June-2002.

05. Progress made during the quarter                      :

Apart from continuation of Creche Centress a new Programme has been taken in the field of Income Generation with the assistance and advice of Mr.Bijoy Patra a SEEDS Volunteer. Depending with the experience of all the SHGs members in the marketing of Badi making, Mr Patra suggested an unique programme to be taken as an income generating activity i.e.growing of farm,fresh mushroom which has a huge market demand in & around Bhubaneswar & Cuttack,(Annexure-I). Hence taking regular help from Mr.Patra we had taken few representatives of SHG members to the Centre for Tropical Mushroom Research & Training under Department of Plant & Pathology, OUAT, Bhubaneswar. Looking to the feasibility & Viability part of the activity the groups showed much interest to take-up the Project. Hence it was decided to provide financial assistance to 06(Six) SHGs for the programme as loan.

Training of SHG members                                 :

As per the advice of the Director, Centre for Tropical Mushroom Research & Training, OUAT,Bhubaneswar a three days programme was organised from 17th June to 19th June-2002 at the said Centre, Bhubaneswar. 18 nos of members (2 from each group) out of 09 nos of SHGs were selected for the training who would be supported in the First Phase. The traineers provided training in preparation of bed for mushroom, control of adequate temperature at the sight & growing of mushroom spawns.

We had arranged the transportation & loadging expenses of the groups during the training period.

06. (a) – Continuation of Creche                           :  The three nos of Creche Centres are Continuing.

(b) – Training of Creche                                 :  We have organised one-day Workshop on preparation

of Low-cost/No cost Teaching/Learning aid. The

programme was conducted by CYSD-DRTC,Bhubaneswar.

(c) – Detail Student list in Centrewise           :      SC              OBC             GEN                   TOTAL

B + G = T    B + G = T     B + G = T           B + G = T

(1)               (2)                 (3)                        (4)

1-Darada                             :  12+19=31           -                    -                12+19=31

2-Hoikera                           : 10+07=17    06+07=13             -                16+14=30

3-Dengasahi                       : 11+08=19    04+07=11             -                15+15=30

(d) – Type of materials used in the centre    :  We have purchased teaching/learning materials for

learners & developed low cost/nocost T/L aid for

joyful learning.

(e) – Village Education Committee             :  The VEC are doing the work smoothly & day-to-day

visit the Centre & solve the problem for the better

running the Creche Centres.

(f) – Do the Creche Worker organised        :  Yes, The village meeting is being organised in

regular meeting ?                                    every quarter where teachers & parents, VEC-

members, Gopinath Juba Sangha staff remain

present & discuss about learners progress &

economic and social development of the village.

(g) – Monitory & Evaluation                       :  The Chief Executive ofo the Institute has

menitored the activities of the programme for its

Progress and proper implementation. The Creche

Workers, VEC members & GJS staff attend the

Monthly meeting & check-up their planning &

finalise annual action plan also has been prepared to

expedite the project smoothly.

VISION FOR NEXT QUARTER      :

Apart from continuation of the Creche Centres the next quarter (July-02 to Sept-02) mailing

Would be devoted to make the new project a success. Although funds has already been

Transferred the Rs.15000/- each to the accounts of 06(six) SHGs in this respect measures

Have been taken to utilize the fund in three phases. Marketing for the products have already

Been finalised with agreement to different houses in both Bhubaneswar & Cuttack.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

UTILISATION CERTIFICATE.

Certified that an amount of Rs. 60,276=00 ( Rupees Sixty thousand tow hundred seventy six )

only has been solely spend by Gopinath Juba Sangha,Alisisasan, Darada, Khurda towards

SEEDS PROJECT from the date 01.01.2001 to 31.03.2002 and the rest amount has been spent

as Lone during the above period.

Bhubaneswar

Date. 17/07/2002.

For R.C. LAL & CO.

Chartered Accountants.

R.C. LAL ,F.C.A

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

BALANCE SHEET AS ON 31.03.2002.

(SEEDS PROJECT)

L I A B I L I T I E S:		Rs._________ P.       A S S E T S:	        Rs._______ P.

GENERAL FUND:				            FIXED ASSETS:

As per last A/c.-1,13,087.40				- Furniture & Fixture

Less: Excess of					  As per Last A/c.       8,375.00

Expenditure over

Income 	(-) 15,271.00		                   CURRENT ASSETS:

(-) 1,28,358.40       Closing Balance :

- Cash in hand		      71.00

- Cash at Bank		    891.00

CURRENT LIABILITIES:

As per last A/c.        1,21,946.00

Add: Lone during

The year 		  15,750.00

1,37,696.00 			        -----------

9,337.60				9,337.60

---------- 				----------

---------- 				----------

AUDITOR’S REPORT

We have audited the foregoing Balance Sheet alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								 For R.C. LAL & CO.

Chartered Accountants.

Dated:- 17/07/2002

R.C LAL.

F.C.A.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

## INCOME AND EXPENDITURE ACCOUNT FOR THE PERIOD FROM 01.01.2002 TO 31.03.2002

## ( SEEDS PROJECT )

## E X P E N D I T U R E S :		     Rs._________ P.    I N C O M E S :   Rs._______ P.

By Bank Interest               9.00

To  Staff Salary :

- Admn. Asst. 			    4,500.00

Excess of Expenditure

Over Income during

- Crèche Worker 		    9,000.00 		the year.                 15,271.00

-  Postage 			       100.00

- Contingency 			    1,650.00

- Bank charges 			         30.00

___________ 			                _________

15,280.00				       15,280.00

------------				        -----------

------------ 				        -----------

AUDITOR’S REPORT

We have audited the foregoing Income and expenditure Account alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								  For R.C. LAL & CO.

Chartered Accountants.

Dated:- 17/07/2002

R.C LAL.

F.C.A.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

RECEIPT AND PAYMENT ACCOUNT FOR THE PERIOD FROM 01.01.2002 TO 31.03.2002.

( SEEDS PROJECT )

R E C E I P T S : 		Rs. __________ P.  P A Y M E N T S :          Rs._______ P.

To  Opening Balance:				      By  Staff Salary :

- Cash in hand			71.00		- Admn. Asst.		4,500.00

- Cash at Bank		          412.00		- Crèche worker 	9,000.00

-  Postage 		   100.00

Bank interest                             9.00              - Contingency               1,650.00

- Bank Charges 	      30.00

Lone received

For General   A/c.		     15,750.00              Closing balance :

- Cash in hand                71.00

- Cash at Bank              891.60

____________ 					_________

16,242.60					16,242.60

----------------					-------------

----------------					-------------

AUDITOR’S REPORT

We have audited the foregoing  Receipt and  Payment  Account  alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								  For R.C. LAL & CO.

Chartered Accountants.

Dated:-  17/07/2002

R.C LAL.

F.C.A.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

BALANCE SHEET AS ON 31.12.2001.

(SEEDS PROJECT)

L I A B I L I T I E S:		Rs._________ P.       A S S E T S:	        Rs._______ P.

GENERAL FUND:				            FIXED ASSETS:

As per last A/c.  16,302.60				- Furniture & Fixture

Less: Excess of					  As per Last A/c.       8,375.00

Expenditure over

Income         	1,29,390.00	 	                  CURRENT ASSETS:

--------------(-) 1,13,087.40       Closing Balance :

- Cash in hand		      71.00

- Cash at Bank		     412.60

CURRENT LIABILITIES:

As per last A/c.           24,622.00

Add: Lone during

The year 		1,13,724.00

1,38,346.00 			        			-----------

Less : Loan	             16,400.00	 1,21,946.00

Refunded.	                ------------------

8,858.60                                  8,858.60

=============				=======

AUDITOR’S REPORT

We have audited the foregoing Balance Sheet alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								 For R.C. LAL & CO.

Chartered Accountants.

Dated:- 17/07/2002

R.C LAL.

F.C.A.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

## INCOME AND EXPENDITURE ACCOUNT FOR THE PERIOD FROM 01.04.2001 TO 31.12.2001

## ( SEEDS PROJECT )

## E X P E N D I T U R E S :		     Rs._________ P.    I N C O M E S :   Rs._______ P.

By Bank Interest              83.00

To  Staff Salary :

-  To Project Co-ordinator          27,000.00

-  Community Organisor            18,000.00

- Admn. Asst. 			  13,500.00

Excess of Expenditure

Over Income during

- Crèche Worker 		   27,000.00 		the year.             1,29,390.00

- Teaching/Learning 	                 6,408.00

materials.

- kitchen garden                          30,000.00

- stationary                                   1,295.00

-  Postage 			        200.00

- Audit Fees                                 2,000.00

- Contingency 			      4,000.00

- Bank charges 			         70.00

___________ 			                _________

1,29,473.00				      1,29,473.00

------------				        -----------

------------ 				        -----------

AUDITOR’S REPORT

We have audited the foregoing Income and expenditure Account alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								  For R.C. LAL & CO.

Chartered Accountants.

Dated:- 17/07/2002

R.C LAL.

F.C.A.

R. C.  LAL  & CO. 				41, ASHOK NAGAR (East)

CHARTERED ACCOUNTANTS					BHUBANESWAR – 751009

ORISSA

Phone : 531695

E-mail : rclal_co@rediffmail.com

# GOPINATH JUBA SANGH

AT: ALISISASAN, PO : DARADA,KHURDA.

RECEIPT AND PAYMENT ACCOUNT FOR THE PERIOD FROM 01.01.2002 TO 31.03.2002.

( SEEDS PROJECT )

R E C E I P T S : 		Rs. __________ P.  P A Y M E N T S :          Rs._______ P.

To  Opening Balance:				      By  Staff Salary :

-  To Project Co-ordinator          27,000.00

-  Community Organisor            18,000.00

- Cash in hand                          150.00		- Admn. Asst. 			  13,500.00

- Cash at Bank                     32,399.60

- Crèche Worker 		  27,000.00

- Bank Interest                          83.00                    	- Teaching/Learning 	                 6,408.00

materials.

- kitchen garden                          30,000.00

- stationary                                   1,295.00

-  Postage 			        200.00

- Audit Fees                                 2,000.00

- Contingency 			      4,000.00

- Bank charges 			         70.00

Loan received

For General   A/c.                  1,13,724.00              Closing balance :

- Cash in hand                            71.00

- Cash at Bank                          412.60

____________ 					           _________

1,46,356.60				                     1,46,356.60

----------------					           --------------

AUDITOR’S REPORT

We have audited the foregoing  Receipt and  Payment  Account  alongwith the cash book and vouchers produced before us for verification and certify that they are in accordance therewith.

Bhubaneswar,								  For R.C. LAL & CO.

Chartered Accountants.

Dated:-  17/07/2002

R.C LAL.,FCA